## Product Backlog
Planned Sprint | 6 | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to Project - Detailed | MUST HAVE | NA | Dinesh kumar | 3- Completed
S1 | S1 | US-002 | Project Workflow Discussed | MUST HAVE | LUCID CHART | Dinesh kumar | 3- Completed
S1 | S1 | US-003 | Project Documentation Discussion | MUST HAVE | NA | Dinesh kumar | 3- Completed
S2 | S2 | US-004 | Data Acquisiton using API | MUST HAVE | Flask | Dinesh kumar | 3- Completed
S2 | S2 | US-005 | Dataset Acquisiton using Web Scraping | SHOULD HAVE | Beautiful soap | Dinesh kumar | 3- Completed
S2 | S2 | US-006 | Collection of Dataset | MUST HAVE | self-collected data, kaggale etc | Dinesh kumar | 3- Completed
S3 | S3 | US-007 | Ocr and pytesseract for text extraction | MUST HAVE | chatgpt | Dinesh kumar | 3- Completed
S3 | S3 | US-008 | Database Integration - Uploading Documents | MUST HAVE | mangodb | Dinesh kumar | 3- Completed
S4 | S4 | US-009 | Preprocessing of the image | MUST HAVE | chatgpt | Dinesh kumar | 3- Completed
S4 | S4 | US-010 | post processing and various image formats | MUST HAVE | chatgpt | Dinesh kumar | 3- Completed
S4 | S4 | US-011 | visulaizations | MUST HAVE | matplotlib and seaborn | Dinesh kumar | 3- Completed
S5 | S5 | US-012 | LLm's | MUST HAVE | hugging face | Dinesh kumar | 3- Completed
S6 | S6 | US-013 | trainig the models and optimizing the performance of the model | MUST HAVE | Transformers and hugging face | Dinesh kumar | 3- Completed
S6 | S6 | US-014 | streamlit | MUST HAVE | chatgpt | Dinesh kumar | 3- Completed
S7 | S7 | US-015 | dealing with frontend backend and LLM integration | MUST HAVE | NA | Dinesh kumar | 3- Completed
S8 | S8 | US-015 | performance optimization | SHOULD HAVE | NA | Dinesh kumar | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7